## Gantt Chart w % Complete
Capston Project Taekowndo Motion tracker
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Create output chart of single kicks | 2020-03-09 | 9 | 2020-03-16 | 8 | 8 | 0 | 100%
| Create function to handle multi-kicks | 2020-03-23 | 23 | 2020-03-30 | 8 | 8 | 0 | 100%
| Create export report of all kicks | 2020-03-30 | 30 | 2020-04-06 | 8 | 8 | 0 | 100%
| Output all kicking data in Python | 2020-04-06 | 6 | 2020-04-13 | 8 | 8 | 0 | 100%
| Test with other users and final report | 2020-04-13 | 13 | 2020-04-20 | 8 | 8 | 0 | 100%
| Increase accracy of the test set | 2020-04-20 | 20 | 2020-04-27 | 8 | 8 | 0 | 100%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1